## Slide 1: Lab 4 – Project Management

## Slide 2: Summary of Lab 3 Insights
Problem: Existing student communication is fragmented and unmoderated.
Goal: Build a structured, moderated forum tailored to IUT.
Feasibility: Achievable using open-source tools within one semester.
Justification: Strong alignment with OSW’s goals and digital transformation needs.

## Slide 3: Work Breakdown Structure – Phases
1. Planning – Team formation, scope definition
2. Analysis – Requirement gathering, stakeholder interviews
3. Design – UI wireframes, database schema
4. Development – Frontend, backend, integration
5. Testing – Unit tests, usability testing
6. Deployment – Server setup, rollout
7. Maintenance – Feedback loop, bug fixes

## Slide 4: Work Breakdown Structure – Sample Tasks
Design: Create wireframes, build database schema
Development: Authentication, thread creation, moderation logic
Testing: Unit tests, bug reports, usability feedback
Deployment: Firebase/Hosting setup, domain mapping

## Slide 5: Gantt Chart Overview
Timeline: ~8–10 weeks total
Planning & Analysis: Week 1–2
Design & Development: Week 2–6
Testing: Week 5–7
Deployment: Week 7–8
Buffer for Maintenance: Week 9–10

## Slide 6: Team Composition
Project Manager – Oversees scheduling and communication
Frontend Developer – UI with React or Flutter
Backend Developer – Node.js/Firebase APIs
Moderator Liaison – Interfaces with OSW policies
Documentation Lead – Maintains reports and guides

## Slide 7: Risk Register
Low user engagement – Promote platform early
Feature delays – Follow Agile sprints
Content overload – Role-based moderation
Notification failure – Monitor Firebase usage
Platform bugs – Allocate testing buffer

## Slide 8: Project Charter Summary – Part 1
Objectives: Structured discussions, OSW-student connection
Scope: Forum, posting, moderation, notifications
Methods: Agile development, weekly reviews

## Slide 9: Project Charter Summary – Part 2
Participants: Developers, moderators, OSW staff
Deliverables: Forum system + Admin tools + Docs
Evaluation: Usage metrics, feedback, survey results

## Slide 10: Proposal Outline
1. Executive Summary
2. Background & Problem
3. Requirements
4. Alternatives Considered
5. Recommended System
6. Design Overview
7. Implementation Plan
8. Testing Plan
9. Evaluation Plan
10. Training & Maintenance

## Slide 11: Viability and Recommendation
Feasible and cost-effective solution
Addresses real communication gaps at IUT
Team is ready and OSW is supportive
Recommendation: Proceed with implementation

## Slide 12: Q&A
Thank you for your time.
We welcome your questions.